WORK PLAN SCHEDULE

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **No.** | **ACTIVITY** | **DATE OF ACTIVITY** | **LOCATION** | **PARTICIPANTS** |
| 1. | Meeting with representatives from international organizations  Objective:   * To present the theme selected by Honduras as President pro tempore (PPT): “Migration, a Shared Responsibility”. | January 2016 | Secretariat of Foreign Affairs and International Cooperation  Tegucigalpa, Honduras | IOM, ICRC, UNHCR, HONDURAN RED CROSS, UNICEF, RCM Technical Secretariat and PPT |
| 2 | Vice-Ministerial Meeting of the Troika  Objective:   * To review the systematization of the planning process of the Technical Secretariat * To agree on the joint work of the Troika | February 17 -19, 2016 | Ministry of Foreign Affairs  San Salvador, El Salvador | Honduras, Mexico, El Salvador and RCM Technical Secretariat |
| 3 | Meeting with Members of RNCOM  Objective:   * To come together and to achieve active participation during the present term of Honduras as PPT | February 23, 2016 | Secretariat of Foreign Affairs and International Cooperation  Tegucigalpa, Honduras | Technical Secretariat of RNCOM and Secretariat of Foreign Affairs and International Cooperation |
| 4 | Meeting with cooperation agencies  Objective:   * To visualize cooperation in implementing the scheduled actions | April 8, 2016 | Secretariat of Foreign Affairs and International Cooperation  Tegucigalpa, Honduras | PPT, ICRC, UNHCR and Norwegian Council for Refugees |
| 5 | Meeting with national institutions involved in migration matters  Objective:   * To provide information about the actions that Honduras will implement as PPT, with the purpose of including them in the meetings of the Regional Consultation Group on Migration | April 12, 2016 | Secretariat of Foreign Affairs and International Cooperation  Tegucigalpa, Honduras | Secretariat of Foreign Affairs and International Cooperation, National Institute of Migration, Office for Children, Adolescents and Family, Inter-institutional Committee Against Commercial Sexual Exploitation and Trafficking in Persons of Honduras |
| 6 | Technical Preparatory Meeting for the Meeting of the Regional Consultation Group on Migration  Objective:   * To review agendas and logistical aspects | April 21, 2016 | Honduras – Costa Rica via Webex | PPT and RCM Technical Secretariat |
| 7 | Meeting of the Regional Consultation Group on Migration and Workshop of the PPT | June 7-10, 2016 (the delegations will arrive on June 6, 2016) | Tegucigalpa, Honduras | Member Countries and RNCOM |
| 8 | Workshop/Dialogue with Civil Society, Migration and Development  Objective:   * To effectively involve civil society in actions implemented under the theme of the PPT | August 30-31, 2016 | Tegucigalpa, Honduras | PPT, TS, civil society |
| 9 | Technical Preparatory Meeting for the XXI Regional Conference on Migration | November 15-17, 2016 | San Pedro Sula, Cortés Honduras | RCM Member Countries, RNCOM |
| 10 | Vice-Ministerial Meeting and handing over the PPT to El Salvador | November 18, 2016 | Omoa, Cortés  Honduras | Vice-Ministers of the RCM Member Countries |